## Slide 1
Plans and Specs
Coordination with Right of Way and Utilities
Presented by
Uyenly Bui, Senior Civil Engineer, City of Irvine
Darrell Hartman, Senior Civil Engineer, City of Irvine
IRWA Summer Refresh Seminar
July 16, 2019

## Slide 2
Planning/Preliminary
Final Design
Construction
PROJECT PHASES INVOLVING RIGHT OF WAY & UTILITIES

## Slide 3
Capital Improvement Project (CIP) development from initial concept to a complete scope of work
Typical “Scope of Services”:
Research/Review
Aerial Topographic Mapping
Utilities Research & Coordination
Environmental Compliance
Technical Studies
Preliminary Design Plans
Preliminary Quantities and Cost Estimates
Identify Right-of-Way Engineering (ROW) Impacts & Costs
Meetings, Presentations and Exhibits
PLANNING/PRELIMINARY ENGINEERING
Notes: The City of Irvine often conduct a preliminary engineering phase on most projects. We invest the time, the staff, and the resources to do our diligence to flush out all issues early that can potentially impact the project. The preliminary engineering phase acts a guidance to pave the way and sets itinerary for the next two phases.

## Slide 4
PLANNING/PRELIMINARY
Identifies stakeholders and project constraints, then “build” alternatives are developed and compared with the “no-build alternative”; concludes with a “preferred” build alternative

## Slide 5
Meetings/Coordination
  Utilities
  Stakeholders (e.g. property owners, Homeowner’s Associations)
  Jurisdictional agencies
  Importance:
  Project/no project
  Impact schedule
  Legal issues
  Monetary costs
  Effort to find solutions
PLANNING/PRELIMINARY

## Slide 6
Environmental Compliance
  California Environmental Quality Act (CEQA)
  National Environmental Policy Act (NEPA) – Federally-funded; federal land
  Technical Studies & Findings – traffic impacts, water quality, biological, noise, geotechnical, air quality, drainage, initial site assessment
PLANNING/PRELIMINARY

## Slide 7
  Phase l/ll studies – Reports prepared for properties that identifies potential or existing environmental contamination liabilities; completed for all parcels involved for appraisal to assess the value of properties
  Phase I – Initial Site Assessment (ISA) report; site description, historical use, search of environmental database, site reconnaissance
  Phase II – Soil samples, soil borings; groundwater tests; only done if recommended by Phase I
PLANNING/PRELIMINARY

## Slide 8
Right of Way (ROW) – Estimate ROW cost for each alternative
PLANNING/PRELIMINARY

## Slide 9
Prepare a preliminary cost estimate to plan a project budget. Identify required studies, jurisdictional regulations, right of way requirements, utility impacts, permits, stakeholders, end users.
Prepare Project Report – Guiding document with next steps; contains preliminary design plans, supporting technical studies, ROW impacts, cost estimate, public involvement, funding sources, and concludes with a justification for the decision
PLANNING/PRELIMINARY

## Slide 10
Final construction documents are developed using preliminary information generated during the Preliminary Engineering phase.
Typical “Scope of Services”:
Base/Preliminary Data Review
Permits
Utilities Identification, Research, Coordination and Notices
Plans
Reports, Studies and Calculations
Environmental and Water Quality Compliance
Special Provisions
Quantities and Cost Estimates
Critical Path Method (CPM) Schedule
Right-of-Way Engineering (ROW) and Legal Descriptions
Meetings, Presentations and Exhibits
FINAL DESIGN

## Slide 11
Initial information necessary to determine Right of Way needs:
Base map
Topographic survey
Existing right of way information
Proposed improvements/geometrics
Utility relocations/modifications
Right of Way Determination – Additional right of way needs are determined by comparing existing right of way information and proposed improvements. Care must be taken to allow for access and construction of the improvements as well as the improvements themselves.
ROW NEEDS

## Slide 12
65% Design:
ROW activity may begin
For tight project schedule - Enables the ROW to be secured in time to meet project schedule
However, may need to go back and acquire additional ROW if any design issues cause a change in ROW requirements as we approach 85% to 100% design
85% to 100% Design:
Ideally ROW Activity should begin at 85-100%
The changes to ROW requirements will be minimal
However, project schedule may suffer due to a later start date for right of way activities
FINAL DESIGN SCHEDULE

## Slide 13
Activities:
Title reports – Property dimensions and encumbrances: liens, easements, etc.
Preparation of ROW maps and legal descriptions by the City’s design consultant
Preparation of the Appraisal – prepared by the City’s appraisal consultant
Preparation of the offer and negotiations for the property by the City
ROW ACTIVITIES

## Slide 14
Title reports – Details liens, easements, etc. on the properties
TITLE REPORT

## Slide 15: ROW EXHIBIT (COMPREHENSIVE)

## Slide 16: ROW EXHIBIT (PROPERTY SPECIFIC)

## Slide 17: PLAT MAPS & LEGAL DESCRIPTIONS

## Slide 18
Fee
Easement
Lease
SECURE RIGHT OF WAY

## Slide 19
Fee – owner retains responsibility for cleanup of all contamination underneath property
Easement – Agency not responsible for contamination below the land
FEE vs. EASEMENT

## Slide 20
Typical easements secured by a local agency include:
EASEMENTS
  Roadway Easements
  Landscape Easements
  Sidewalk Easements
  Drainage Easements
  Wall or Footing Easements
  Aerial Easements
Non-standard easements may include:
General deed language will state “…a perpetual easement for public street and utility purposes…”
More specific deed language will state “…a perpetual easement to plant, maintain, replace or remove landscaping…”

## Slide 21
Lease for use of a property for a period of time; renewable
(e.g. City of Irvine leases Southern California Edison’s property for use as a trail)
LEASE
Walnut Trail

## Slide 22
Fee Acquisition – recorded deed with the legal descriptions and plat map describing acquired property, transferring to the new owner’s name
Jamboree Road/I-5 Interchange
FEE ACQUISITION

## Slide 23
Permanent Easement – recorded document that new owner has a right for use an identified area for a specific purpose, described in a legal description and plat map
PERMANENT EASEMENT

## Slide 24
Temporary construction easement (TCE) – Compensated, non-recorded document granting the right to enter a specific area of a property for construction activities; may mention work hours, timeframe before TCE expires, advanced notification, re-establish property to existing condition when done.
  TCE for roadway improvements, TCE for mitigation areas
TEMPORARY CONSTRUCTION EASEMENT

## Slide 25
Permit to Enter and Construct – Non-recorded permit used when project improvement is for the benefit of the property owner; no condemnation.
RIGHT OF ENTRY / PERMIT TO ENTER & CONSTRUCT

## Slide 26
Contact Dig-A-Lert for listing of utilities in project vicinity
Utility Notices:
  Preliminary (request for utility maps); set up utility log sheet
UTILITIES COORDINATION

## Slide 27
Second Notice – Review plans for accuracy of utilities shown; determine prior rights; pothole crossings to determine if any conflicts
UTILITIES COORDINATION

## Slide 28
Third Notice (Final) – Notice to Relocate
UTILITIES COORDINATION

## Slide 29
If project is federally-funded or on State’s property, a Right of Way Certification is required (Caltrans Right of Way Manual, Chapter 14). General requirements include:
  Final Project Plans and Specifications
  Caltrans Right of Way Certification
  Project Engineer’s Utility Certification
  Utility “Notice to Owners”
  Project Environmental Documents
  Right of Way Agreements
FEDERAL FUNDING/STATE RIGHT OF WAY

## Slide 30
Project is awarded to Contractor who to builds the improvements and delivers a completed facility based on final construction documents.
Stake ROW/TCE lines in the field and to make the contractor aware of the construction area he has to work within.
Include property owner provisions in the project Special Provisions.
Include utility durations in the project Special Provisions.
CONSTRUCTION

## Slide 31
Contractor shall comply with specific property requirements, included in the contract special provisions. If applicable, include the following information:
  Property address
  Contact information
  Special notice requirements
  Special access requirements
  Durations/timelines
  Modified insurance limits
  Specific instructions included in right of way agreements
SPECIFIC PROPERTY REQUIREMENTS

## Slide 32
Contractor shall comply with specific utility requirements, included in the contract special provisions. If applicable, include Utility Contact Table and additional utility specific information
SPECIFIC UTILITY REQUIREMENTS
Utility Contact Table
Utility Specific Information

## Slide 33
RIGHT OF WAY CONSTRUCTION IMPACTS
Caltrans I-5 Segment “C”
RCB at Euclid Plaza
Lincoln OC Utilities

## Slide 34
Plans and Specs
Coordination with Right of Way and Utilities
Questions?
IRWA Summer Refresh Seminar
July 16, 2019