## Slide 2: Right of Way Certification
By: Ricky Rodriguez &
Evangelina Washington

## Slide 3: General Overview
- What/When/Why
- Levels of Right of Way Certification
- Methods of Project Delivery
- Local Agency R/W Certifications
- Local Agency Certification Exhibits

## Slide 4: What is Right of Way Certification?
Written statement that summarizes the status of all right of way related matters pertaining to a proposed construction project (PS&E).
Documentation that the construction package is ready for advertising
Certifies that real property interests have been or are being secured; physical obstructions have been (or will be) removed, relocated, or protected as required for construction, operation and maintenance; acquisitions and RAP were conducted in accordance with applicable state/federal laws and procedures.

## Slide 5: When is a R/W Certification required?
All projects except emergency re-opening of transportation facilities that do not require a PS&E package require a R/W Certification including:
  Any highway project benefiting from either federal funds or state funds requiring CTC allocation approval
  Projects with no R/W requirements
  Projects with only utility involvements (even city owned)
  Acquisition parcels (either permanent or temporary) including railroad

## Slide 6: Why is a R/W Certification necessary?
R/W Certification is required per Code of Federal Regulations
R/W Certifications are essential for project delivery.
  Certification is R/W’s main deliverable
  Cannot advertise without R/W Certification
R/W Certification is a mechanism to ensure compliance with federal and state regulations.
Federal funds cannot be authorized without the R/W Certification.

## Slide 7: R/W Certification Levels
Certification 1
  Full legal (title) and physical possession of all right of way
  Can advertise and award
Certification 2 – similar to Cert. No. 1 except:
  Right to occupy and use remaining parcels is by virtue of a Possession and Use Agreement, permit, license, or an approved R/W Contract with effective possession date and funds must be on deposit in an escrow account
  Can advertise and award

## Slide 8: R/W Certification Levels (cont’d)
“Conditional” Certification 3
  Do not have legal possession or right of occupancy on one or more remaining parcels; however, there is a realistic date certain of when control will be obtained. At minimum, parcels not yet acquired must have been adopted by the California Transportation Commission (CTC) with a resolution of necessity (RON).
  Relocation Assistance & replacement housing has been made available to impacted persons/businesses
  Utility Relocations and/or Railroad deliverables not yet completed
  Justification Memorandum to HQ’s must be submitted with the R/W Certification as to why a Conditional R/W Certification 3 is needed.
  Can advertise but cannot award until R/W Certification is elevated (upgraded) to a R/W Certification 1 or 2 (minimum of 15 working days prior to bid opening).

## Slide 9: R/W Certification Levels (cont’d)
Certification 3 with Work-Around
  An agreement has been reached with owner, or a RON has been obtained, but, no physical possession until a later date.
  Orders for Possession may have been issued and/or served but are not yet effective.
  Only to be used in extraordinary circumstances; HQ’s Memorandum of justification is required.
  Can advertise and award (bid package must identify work-arounds)
  Certification allows for advertisement and physical construction to commence by working around occupants remaining within the right of way.
  Must be updated 15 days prior to bid opening
Cert. 3 & Cert. 3 with work-around must be approved by HQ and, if required FHWA per the Stewardship & Oversight Agreement)

## Slide 10: Methods of Project Delivery
Design Bid Build
  Traditional method
  Linear progression
  Plan, design, and complete R/W prior to advertise and award
Alternative Methods
  Design Build (DB)
  Construction Manager/General Contractor (CM/GC)

## Slide 11: Methods of Project Delivery (cont’d)
Design Build
  Design and construction phases of a project are combined into one contract and approved for construction
  Accelerates project delivery by allowing design and construction teams to work together early-on to improve constructability
  DB’s can transfer risk to either the DB contractor (design & construction) or to Caltrans/Local Agency (acquiring r/w)
  Allows phased delivery of R/W deliverables before and during construction
Construction Manager/General Contractor (CM/GC)
  Two phase contracting method (RFP~Design~Construction)
  CM is hired as a consultant for project design and may be hired to complete construction as GC.

## Slide 12: Methods of Project Delivery (cont’d)
DB and CM/GC R/W Certification Process
  Submittal of a Right of Way Statement that will provide status
  of all right of way activities
  Can certify segments of a project as release for construction packages are approved
  R/W Certifications will meet the requirements for a Cert. 1 or 2
  (any deviations from a Cert 1 or 2 will require FHWA approval)
  Presently, DB and CM/GC Certifications require Caltrans HQ’s approval

## Slide 13: Local Agency R/W Certifications
Local Agency prepares Right of Way Certification on federally assisted projects for both on-system and off-system projects
A Right of Way Certification is completed even if no right of way is required for the project.
When property rights are required for local federal-aid project, the agency to certify rights acquired in conformance with Uniform Act.
It is crucial that Local Agencies adhere to CFR’s, Caltrans R/W & Local Assistance Manuals so federal funds are not jeopardized.
Local Agency R/W Cert.’s are reviewed and accepted by Caltrans
R/W Cert. 3’s require acceptance by Caltrans and approval by FHWA

## Slide 14: Local Agency R/W Certification Exhibits
On-System
(R/W Manual)
17-EX-9, Design-Build - Project Right of Way Statement
17-EX-10, Design-Build Certification
17-EX-13, Construction Manager/General Contractor (CM/GC) Certification
17-EX-18, Right of Way Certification
Off-System
(Local Assistance Manual)
Exhibit 13-A: Short Form. Used when there is no acquisitions but there are utility cover adjustments
Exhibit 13-B: Right of Way Certification Local Assistance